## Sheet1
| Arctic Thread: | Agile Backlog
| Team Members: | Liam De Rivers, Mark Moerkerken, Seth VanNiekerk
# | Link | Description | Hours est. | Iteration Added | Added By | Status | # | Link | Description | Hours est. | Iteration Added | Added By | Status | # | Link | Description | Hours est. | Iteration Added | Added By | Status
High Priority | [6 empty] | Medium Priority | [6 empty] | Low Priority
[7 empty] | M25 | https://github.com/Arctic-Thread/Capstone/issues/25 | Business No. / HST | 5 | 1 | Team Meeting | FALSE | L37 | https://github.com/Arctic-Thread/Capstone/issues/37 | Permission from Business To Register | 2 | 1 | Team Meeting | FALSE
[7 empty] | M38 | https://github.com/Arctic-Thread/Capstone/issues/38 | Image Scaling | ? | 1 | Team Meeting | TRUE | L39 | https://github.com/Arctic-Thread/Capstone/issues/39 | Price Matching Items | 2021-02-03 | 1 | Team Meeting | FALSE
[7 empty] | M44 | https://github.com/Arctic-Thread/Capstone/issues/44 | 3rd Party Payment Methods | 3 | 1 | Liam | TRUE | L40 | https://github.com/Arctic-Thread/Capstone/issues/40 | Pickup Windows | 3 | 1 | Team Meeting | FALSE
[7 empty] | M81 | https://github.com/Arctic-Thread/KurbSide/issues/81 | Administrative Password required for destructive edits & deletes | 2 | 2 | Liam | FALSE | L41 | https://github.com/Arctic-Thread/Capstone/issues/41 | Allow/Facilitate Returns | 2021-02-03 | 1 | Team Meeting | FALSE
[14 empty] | L62 | https://github.com/Arctic-Thread/Capstone/issues/62 | Promoted Business On Home Page | 3 | 1 | Liam | FALSE
[14 empty] | L80 | https://github.com/Arctic-Thread/Capstone/issues/80 | Postal Code Validation | 2 | 1 | Liam | FALSE
[14 empty] | L142 | https://github.com/Arctic-Thread/KurbSide/issues/142 | Mix & Match in carts | 3 | 2 | Liam | FALSE