## Sheet1
| Arctic Thread: | Release Plan Summary
| Team Members: | Liam De Rivers, Mark Moerkerken, Seth VanNiekerk
|  | Iteration #1 | Iteration #2 | Iteration #3
| Due: | February 25th | March 18th | April 8th
# | Feature
1 | Business Registration | 2
2 | Login (All Types) | 1
3 | Mailing System | 2
4 | Business Controls | 2
5 | Catalogue Listing | 2
6 | User Registration |  | 2
7 | Browse Businesses |  | 2
8 | Browse Catalouges |  | 2
9 | View Item Information |  | 1
10 | Cart |  | 3
11 | Business Order Process |  |  | 2
12 | "Checkout" |  |  | 2
13 | Customer Notifier |  |  | 2
14 | Catalouge Assets |  |  | 1
15 | Business Reviews |  |  | 2
| Work Effort In Hours |  |  |  | 28